## G06_Chí Bảo
n
Project Code | SWP-G05 | Project Topic | AutoWash Pro - Hệ thống quản lý rửa xe với đặt lịch trước & loyalty | Group Name | Group 1 | Leader |  | GitHub Repo
Tech Stack | React + Spring Boot + SQL Server | Main Domain | Car Wash Management / Booking / Loyalty | Members |  | Mentor |  | Deployment Link
Sprint/Week |  | Last Updated |  | Overall Note
Functional Requirements / User Stories - mỗi dòng là một chức năng nhỏ, có thể giao việc, test và demo.
Req ID | Module | Functional Requirement / User Story | Actor | Priority | Acceptance Criteria | Test / Demo Scenario | UI / API / Page | Owner | Status | Evidence Link / Note
FR-AUTH-001 | Authentication | Customer can register an account using phone number or email and password. | Customer | Must | New customer account is created successfully with Active status and can be used to login. | Enter valid phone/email and password on Register screen → Submit → Login with new account → verify access granted. | Register page / POST /auth/register |  | Not Done
FR-AUTH-002 | Dashboard | Customer can log in using phone number or email and password. | Customer | Must | Customer is redirected to home screen with valid session token after correct credentials. | Enter valid credentials → login → verify session token exists. Enter wrong password → verify error message 'Invalid credentials'. | Login page / POST /auth/login |  | Not Done
FR-AUTH-003 | Authentication | Admin can log in using admin credentials. | Admin | Must | Admin is redirected to Admin Dashboard. Non-admin accounts cannot access admin pages. | Login with admin account → verify dashboard. Login with customer account → try /admin URL → verify redirect/403. | Admin Login page / POST /auth/login |  | Not Done
FR-VEH-001 | Customer Vehicles | Customer can add a new vehicle by providing license plate, vehicle type, and name. | Customer | Must | New vehicle appears in the customer's vehicle list. Other customers cannot see it. | Login as Customer A → add vehicle plate '59A1-12345', type 'Motorbike' → verify it appears in My Vehicles list. | My Vehicles page / POST /api/vehicles |  | Not Done
FR-VEH-002 | Customer Vehicles | Customer can view the list of their own vehicles. | Customer | Must | Only vehicles belonging to the logged-in customer are displayed. | Login as Customer A (has 2 vehicles) → open My Vehicles → verify 2 vehicles shown. Login as Customer B → verify Customer A's vehicles not visible. | My Vehicles page / GET /api/vehicles |  | Not Done
FR-VEH-003 | Customer Vehicles | Customer can edit the details of their own vehicle. | Customer | Must | Vehicle details are updated and changes are reflected immediately in the list. | Login → select a vehicle → edit vehicle name → save → verify new name shows in list. | My Vehicles page / PUT /api/vehicles/{id} |  | Not Done
FR-VEH-004 | Customer Vehicles | Customer can delete a vehicle they own. | Customer | Must | Deleted vehicle no longer appears in the vehicle list. | Login → select a vehicle → delete → confirm → verify vehicle removed from list. | My Vehicles page / DELETE /api/vehicles/{id} |  | Not Done
FR-BOOK-001 | Booking | Customer can create a wash booking by selecting a vehicle, service, date, and time slot. | Customer | Must | Booking is created with status 'Pending' and appears in the customer's booking history. | Login → select vehicle '59A1-12345' → select service 'Basic Wash' → select a valid time slot → confirm → verify booking in history with Pending status. | Booking page / POST /api/bookings |  | Not Done
FR-BOOK-002 | Booking | System enforces tier-based advance booking window when customer selects a booking date. | System | Must | Booking date within the customer's allowed window is accepted. Date outside the window is rejected with an error message. | Today = 01/06. Member selects 12/06 (11 days ahead) → system rejects. Gold selects 12/06 (11 days ahead) → system rejects. Platinum selects 12/06 (11 days ahead) → system accepts. | Booking service / validation layer / POST /api/bookings |  | Not Done
FR-BOOK-003 | Booking | System blocks booking if the selected time slot has reached full capacity. | System | Must | Customer is shown an error 'This time slot is full. Please choose another slot.' and booking is not created. | Set slot capacity = 3. Create 3 bookings for 08:00. 4th customer tries to book 08:00 → verify rejection message appears. | Booking page / POST /api/bookings / slot availability check |  | Not Done
FR-BOOK-004 | Booking | Customer can view their booking history with status. | Customer | Must | All bookings of the logged-in customer are shown with correct statuses (Pending, Confirmed, Completed, Cancelled). | Login → open Booking History → verify all past and upcoming bookings are listed with correct status. | Booking History page / GET /api/bookings/my |  | Not Done
FR-BOOK-005 | Booking | Customer can cancel a Pending or Confirmed booking. | Customer | Should | Booking status changes to Cancelled and the time slot becomes available again. | Login → select a Pending booking → cancel → verify status changes to Cancelled. Verify another customer can now book that slot. | Booking History page / PUT /api/bookings/{id}/cancel |  | Not Done
FR-BOOK-006 | Booking | Admin can view all bookings and filter by date, status, or customer. | Admin | Must | All bookings are displayed. Filters correctly narrow down results. | Login as Admin → open Booking Management → filter by status 'Pending' → verify only Pending bookings appear. | Admin Booking Management page / GET /api/admin/bookings |  | Not Done
FR-BOOK-007 | Booking | Admin can update a booking status (Confirm, Complete, Cancel). | Admin | Must | Booking status is updated. Completing a booking triggers loyalty point addition. | Admin selects a Confirmed booking → marks as Completed → verify status updated and customer's point balance increased. | Admin Booking Management page / PUT /api/admin/bookings/{id}/status |  | Not Done
FR-LYL-001 | Loyalty | System automatically adds loyalty points when admin marks a booking as Completed. | System | Must | One point transaction record is created. Customer's available point balance increases correctly based on point rate. | Point rate = 1 pt per 10,000 VND. Admin completes booking with final amount 120,000 VND → verify customer gains 12 points and transaction record exists. | Admin booking page / loyalty service layer / POST /api/points/add |  | Not Done
FR-LYL-002 | Loyalty | Customer can view their current point balance and point transaction history. | Customer | Must | Point balance is accurate. Transaction history shows date, amount, and reason for each entry. | Login → open My Points page → verify balance matches sum of transaction history entries. | My Points page / GET /api/points/me |  | Not Done
FR-LYL-003 | Loyalty | System automatically upgrades or downgrades customer tier based on monthly review of accumulated points. | System | Must | Customer tier changes correctly when points threshold is met or dropped. Tier change is logged. | Set Silver threshold = 500 pts. Customer earns 500th point → next monthly review → verify tier changed to Silver. | Loyalty service / monthly scheduled job / GET /api/customers/{id}/tier |  | Not Done
FR-LYL-004 | Loyalty | Customer's points expire automatically after 12 months of inactivity. | System | Should | Points older than 12 months with no activity are marked as expired and deducted from balance. | Set a point transaction dated 13 months ago → run expiry job → verify those points are expired and balance updated. | Loyalty service / expiry scheduled job |  | Not Done
FR-LYL-005 | Loyalty | Customer can redeem points for a discount or free wash at checkout. | Customer | Must | Redeemed points are deducted from balance. Booking price is reduced by the equivalent discount amount. | Customer has 100 points (= 10,000 VND discount). At checkout select 'Redeem 100 points' → verify booking cost reduced by 10,000 VND and balance drops by 100. | Booking checkout page / POST /api/points/redeem |  | Not Done
FR-TIER-001 | Tier | System assigns the correct advance booking window based on customer tier (Member: 7 days, Silver: 10 days, Gold: 12 days, Platinum: 14 days). | System | Must | Each tier's booking window is enforced: Member cannot book >7 days ahead; Platinum can book up to 14 days ahead. | Today=01/06. Member books 09/06 (8 days): reject. Silver books 11/06 (10 days): accept. Gold books 13/06 (12 days): accept. Platinum books 15/06 (14 days): accept. | Booking service validation / GET /api/customers/{id}/tier |  | Not Done
FR-TIER-002 | Tier | Higher-tier customers receive priority in the booking queue for the same time slot. | System | Should | When capacity is limited, Platinum and Gold customers' bookings are accepted before Member-tier customers. | Slot capacity=1. Platinum and Member both try to book 10:00 simultaneously → Platinum booking accepted; Member gets 'slot full' error. | Booking service / queue priority logic |  | Not Done
FR-PROMO-001 | Promotion | Admin can create a promotion with name, discount value, start/end date, and eligible customer tiers. | Admin | Should | Promotion is saved with correct details and visible only to customers of the selected tiers within the active date range. | Create promotion 'Silver Weekend' for Silver/Gold/Platinum tiers, valid 01/06–15/06. Login as Member → verify promotion not shown. Login as Silver → verify promotion visible on 10/06. | Admin Promotion page / POST /api/promotions |  | Not Done
FR-PROMO-002 | Promotion | Customer can view promotions available to their tier. | Customer | Should | Only promotions where current date is within active range and customer's tier is eligible are shown. | Login as Silver on 10/06 → open Promotions page → verify Silver-eligible active promotions are listed. Login as Member → verify Silver-only promotions are hidden. | Promotions page / GET /api/promotions/available |  | Not Done
FR-PROMO-003 | Promotion | Customer can apply a promotion code at booking checkout to receive a discount. | Customer | Should | Discount is applied to the booking total. Ineligible or expired promotions are rejected with error message. | Apply valid Silver promo code as Silver customer → verify discount applied. Apply same code as Member → verify 'Not eligible' error. Apply expired promo code → verify 'Promotion expired' error. | Booking checkout page / POST /api/bookings/apply-promo |  | Not Done
FR-DASH-001 | Admin Dashboard | Admin can view a dashboard showing total bookings, revenue, and new customers for a selected period. | Admin | Should | Dashboard displays accurate aggregated figures. Changing the date filter updates the metrics accordingly. | Login as Admin → open Dashboard → select 'This month' → verify booking count, revenue, and new customer count are correct. | Admin Dashboard page / GET /api/admin/dashboard?period=month |  | Not Done
FR-DASH-002 | Admin Dashboard | Admin can configure loyalty point rates and tier upgrade thresholds. | Admin | Must | Updated point rate and tier thresholds are saved and applied to all future transactions and monthly tier reviews. | Admin sets point rate to 1pt/10,000 VND and Silver threshold to 500pts → admin completes a 100,000 VND booking → verify customer gains 10 points. | Admin Settings page / PUT /api/admin/loyalty-config |  | Not Done

## G06_Rules
GROUP 06 - BUSINESS RULES
Hướng dẫn: điền thông tin dự án/nhóm ở phần trên. Phần dưới chỉ ghi các mục đủ nhỏ để code được, test được, demo được. Status chỉ chọn Not Done hoặc Done.
Project Code | SWP-G06 | Project Topic |  | Group Name | Group 6 | Leader |  | GitHub Repo
Tech Stack |  | Main Domain |  | Members |  | Mentor |  | Deployment Link
Sprint/Week |  | Last Updated |  | Overall Note
Business Rules - mỗi dòng là một luật nghiệp vụ rõ điều kiện, hành động, ngoại lệ và cách kiểm tra.
Rule ID | Related Req ID | Module | Rule Type | Business Rule Statement | Condition / Trigger | System Action / Expected Result | Exception / Error Message | Test Case / Example Data | Status | Evidence Link / Note